## Start here
Earth5R CSR Impact Assessment Workbook
Free to use and adapt, with credit: CSR Impact Assessment Handbook, Earth5R Guides No. 05
https://earth5r.org/guides/csr-impact-assessment-handbook/
How to use: yellow cells are inputs. Green cells calculate. Example data is filled in so you can see how each sheet works; overwrite it with your own.
Sheets
1 Applicability: is impact assessment mandatory for each CSR project? (Rule 8(3)(a))
2 Cost cap: how much impact assessment spend can be booked as CSR this year (Rule 8(3)(c))
3 Sample size: survey sample for a given population, confidence level and margin of error
4 Evaluation matrix: OECD-DAC criteria, evaluation questions, indicators, sources and methods
5 Scoring: weighted score out of 100 across the six criteria, with a rating band
6 SROI: social return on investment with deadweight, attribution, displacement, drop-off and a sensitivity test
7 Agency selection: compare independent agencies on weighted criteria, with an independence gate
8 Action tracker: recommendations, management response, owner, due date and status
9 Calendar: a 12-month impact assessment cycle aligned to the annual report on CSR
The rules in brief (Companies (CSR Policy) Rules, 2014, as amended)
Rule 8(3)(a): a company with average CSR obligation of ₹10 crore or more in the three immediately preceding financial years must get an independent impact assessment of CSR projects with outlays of ₹1 crore or more, completed not less than one year before the study.
Rule 8(3)(b): reports go before the Board and are annexed to the annual report on CSR. MCA accepts a web link to the full reports plus an executive summary in the annual report.
Rule 8(3)(c): impact assessment spend may be booked as CSR up to 2% of total CSR expenditure for the year or ₹50 lakh, whichever is higher (amended 20 September 2022).
Projects funded through zero coupon zero principal instruments on a Social Stock Exchange are exempt from impact assessment (Rule 4A, inserted 27 May 2026).
Not legal advice. Check the current rules and MCA FAQs, and involve your company secretary. Figures in example rows are illustrative only.

## 1 Applicability
Is impact assessment mandatory?
Rule 8(3)(a): average CSR obligation ≥ ₹10 crore in the 3 preceding FYs AND project outlay ≥ ₹1 crore AND project completed ≥ 1 year before the study.
CSR obligation (2% amount), ₹ crore
Financial year −1 | 12.4
Financial year −2 | 11.1
Financial year −3 | 9.75
Average of the three years
Company in the mandatory regime?
Threshold (₹ crore) | 10
CSR project | Outlay (₹ crore) | Completion date | Planned study start | Outlay ≥ ₹1 crore? | Completed ≥ 1 year before study? | Completed on/after 22 Jan 2021? | Impact assessment | Notes
Women’s skilling centres, 3 districts | 2.8 | 2024-03-31 | 2025-07-01
Mobile health units | 1.35 | 2025-03-31 | 2025-07-01 |  |  |  |  | Wait until April 2026
School WASH upgrades | 0.85 | 2024-03-31 | 2025-07-01 |  |  |  |  | Below ₹1 crore
River cleanup and waste segregation | 1.45 | 2024-11-30 | 2026-01-15
Formulas:
Completed ≥ 1 year before study? = IF(OR([Completion date]="",[Planned study start]=""),"",IF([Planned study start]>=EDATE([Completion date],12),"Yes","No"))

## 2 Cost cap
How much impact assessment spend can be booked as CSR?
Rule 8(3)(c) as amended on 20 September 2022: up to 2% of total CSR expenditure for the financial year or ₹50 lakh, whichever is higher.
Total CSR expenditure for the financial year (₹ crore) | 34.75
Percentage limit | 2%
Fixed limit (₹ crore) | 0.5
Maximum impact assessment spend bookable as CSR (₹ crore) |  | The higher of the two limits
Impact study | Budget (₹ crore) | Agency / status
Women’s skilling centres | 0.12 | Shortlisting
River cleanup and segregation | 0.09 | ToR drafted
Total planned impact assessment spend (₹ crore)
Headroom under the cap (₹ crore)
Within the cap?
Note: this spend is separate from, and in addition to, the 5% cap on CSR administrative overheads (MCA FAQ 9.5). Report it in the annual report on CSR under "Amount spent in Impact Assessment, if applicable".

## 3 Sample size
Survey sample size calculator
Simple random sample with finite population correction, design effect and expected response rate.
Population: number of beneficiaries (N) | 1020 | Everyone the project reached, or the group you want to describe
Confidence level | 95% | Choose 90%, 95% or 99%. 95% is the usual choice
Margin of error | 7% | 5% to 10% is typical for CSR studies; smaller costs more
Expected proportion (p) | 50% | 0.5 gives the most conservative (largest) sample
Design effect | 1 | 1.0 for simple random sampling; 1.5 to 2.0 if you sample villages or centres first (clusters)
Expected response rate | 90% | Allow for people who cannot be found or decline
z value
Sample for an infinite population (n₀)
After finite population correction
After design effect
Completed interviews needed
Interviews to attempt (allowing for non-response)
Sample as share of population
Quick reference: completed interviews needed (p = 0.5, design effect 1) | Population | 95% ±5% ¦ 95% ±7% ¦ 95% ±10%
100
300
1000
3000
10000
50000
Qualitative work is chosen, not calculated: plan focus group discussions (8 to 12 people each) with each main beneficiary group, and key informant interviews with implementers, local officials, employers or health workers. Stop when new interviews stop adding new themes.

## 4 Evaluation matrix
Evaluation matrix (OECD-DAC criteria)
Example: a women’s skilling and placement programme. Replace the questions and indicators with your own project’s.
Criterion | Key question (OECD-DAC) | Evaluation question for this project | Indicator | Baseline | Endline / result | Data source | Method
Relevance | Is the intervention doing the right things? | Did the trades offered match local job demand and trainees’ needs? | % trainees who say the course matched their goals; employer demand for the trades |  |  | Trainee survey; employer interviews; labour market data | Survey, KIIs, desk review
Coherence | How well does the intervention fit? | Did the programme link to government schemes and other skilling efforts in the district? | Number of trainees linked to schemes (e.g. certification, credit) |  |  | Programme records; district officials | Records review, KIIs
Effectiveness | Is the intervention achieving its objectives? | Did trainees complete, get certified and get placed as planned? | Completion rate; certification rate; placement rate at 3 months |  |  | MIS; placement records; trainee survey | Records review, survey
Efficiency | How well are resources being used? | Was cost per trainee placed reasonable, and was delivery on time and on budget? | Cost per trainee trained and per trainee placed; budget utilisation |  |  | Financial records; MIS | Cost analysis
Impact | What difference does the intervention make? | Did incomes, confidence and decision-making change, for whom, and were there unintended effects? | Change in monthly income; % reporting say in household decisions; negative effects reported |  |  | Trainee survey (with comparison group if possible); FGDs | Pre-post survey, FGDs, case studies
Sustainability | Will the benefits last? | Are trainees still employed after 12 months, and can centres run without CSR funding? | % still employed at 12 months; share of centre costs covered by other sources |  |  | Tracer survey; centre accounts | Tracer survey, KIIs
Source for the key questions: OECD DAC Network on Development Evaluation, Better Criteria for Better Evaluation (2019).

## 5 Scoring
Project score out of 100
Score each criterion 1 to 4 using the rubric below. Weights are editable and should add up to 100.
Criterion | Weight | Score (1 to 4) | Weighted score | Evidence / reason for score
Relevance | 15 | 4 |  | Trades chosen from a demand survey; strong fit with trainee goals
Coherence | 10 | 3 |  | Linked to state certification; weaker link to credit schemes
Effectiveness | 25 | 3 |  | Placement 72% against 75% target
Efficiency | 15 | 3 |  | Cost per placement within plan; one centre opened late
Impact | 20 | 3 |  | Median income up; no comparison group, so attribution is moderate
Sustainability | 15 | 2 |  | Drop-off after placement; centres depend on CSR funding
Total
Weights check
Rating
Score | Meaning |  |  | Rating bands
4 | Fully met, with strong evidence |  |  | 80 to 100: Highly satisfactory
3 | Largely met; minor gaps |  |  | 65 to 79: Satisfactory
2 | Partly met; significant gaps |  |  | 50 to 64: Partly satisfactory
1 | Not met, or no credible evidence |  |  | Below 50: Unsatisfactory

## 6 SROI
Social return on investment (SROI)
Value each outcome, remove what would have happened anyway, and discount future years. Do not overclaim: test the result.
Investment (CSR spend on the project, ₹) |  | 20000000
Discount rate |  | 6.5% | Use a stated rate, e.g. a long-term government bond yield
Sensitivity: multiply attribution by |  | 1.5 | 1.5 = attribution increased by 50%
Outcome | Stakeholder | Indicator | Quantity (people) | Financial proxy (₹ per person per year) | Proxy source | Duration (years) | Deadweight % | Attribution % | Displacement % | Drop-off % per year | Impact in year 1 (₹) | Present value (₹) | Impact yr 1, sensitivity (₹) | Present value, sensitivity (₹)
Higher earnings from a job | Placed trainees | Change in monthly income | 600 | 60000 | Survey: median gain ₹5,000/month | 3 | 20% | 25% | 5% | 20%
Savings on health costs | Trainee households | Out-of-pocket spend avoided | 400 | 6000 | Survey; district health data | 2 | 30% | 30% | 0% | 30%
Confidence and say at home | Trainees | % reporting more say in decisions | 500 | 4000 | Stated preference, FGDs | 2 | 25% | 40% | 0% | 50%
Total present value of social value (₹)
SROI ratio (₹ of social value per ₹1 invested) | [10 empty] | Base |  | Sensitivity
Change under the sensitivity test
Deadweight: what would have happened anyway. Attribution: the share of change due to others (government, family, other NGOs). Displacement: benefits that simply moved from someone else. Drop-off: how much the effect fades each year after the first. Principles: Social Value International, Principles of Social Value (involve stakeholders, understand what changes, value what matters, include only what is material, do not overclaim, be transparent, verify the result, be responsive).

## 7 Agency selection
Choosing an independent agency
Rule 8(3)(a) requires an independent agency; the Board decides the eligibility criteria (MCA FAQ 9.4). Score 1 (weak) to 5 (strong).
Gate: agency is independent of the implementing agency and has no conflict of interest (Yes/No)
Independence confirmed |  | Yes | Yes | No
Criterion | Weight | Agency A | Agency B | Agency C | What good looks like
Relevant impact assessment experience | 20 | 4 | 5 | 3 | Similar projects and sectors; sample reports you can read
Quality of proposed method | 25 | 4 | 3 | 4 | Clear evaluation questions, sample design, comparison or baseline, mixed methods, limitations stated
Team and field capacity | 15 | 3 | 4 | 4 | Named team lead; trained enumerators; local languages; data quality checks
Ethics and data protection | 10 | 4 | 3 | 3 | Informed consent, child safeguarding, anonymised data, secure storage
Local reach | 10 | 3 | 4 | 5 | Can reach the project villages or wards within the timeline
Cost | 15 | 3 | 4 | 5 | Within the Rule 8(3)(c) cap; transparent day rates and field costs
Timeline | 5 | 4 | 3 | 4 | Report in time for the CSR Committee and Board calendar
Weighted score out of 100
Rank
Weights check

## 8 Action tracker
Recommendations and management response
An assessment is only useful if someone acts on it. Review this sheet at every CSR Committee meeting.
# | Impact study | Recommendation | Accepted? | Management response | Owner | Due date | Status | Days overdue
1 | Women’s skilling centres | Track trainees for 12 months after placement to measure drop-off | Yes | Tracer calls at 3, 6 and 12 months from next batch | Programme lead | 2026-06-30 | In progress
2 | Women’s skilling centres | Add a comparison group in the next assessment | Partly | Baseline of next batch plus waitlisted applicants as comparison | CSR head | 2026-09-30 | Not started
3 | River cleanup | Publish monthly tonnage by waste type | Yes | Dashboard on website | Partner NGO | 2026-03-31 | Done
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Formulas:
Days overdue = IF(OR([Due date]="",[Status]="Done"),"",MAX(0,TODAY()-[Due date]))

## 9 Calendar
A 12-month impact assessment cycle
For an April to March financial year. Shift the months if your year differs.
Month | Step | Who | Output
April | List projects that meet Rule 8(3)(a): outlay ≥ ₹1 crore, completed at least a year ago. Add strategic projects to assess voluntarily. | CSR team, company secretary | Assessment list (sheet 1)
May | Agree evaluation questions and budget within the cap; issue terms of reference to three or more agencies. | CSR team, CSR Committee | Terms of reference; budget (sheet 2)
June | Score proposals, confirm independence, appoint agency. | CSR team, procurement | Agency scorecard (sheet 7)
July | Inception report: method, sample, tools, ethics, timeline. Share tools with implementing partner. | Agency | Inception report
August | Pilot tools in local languages; fieldwork begins. | Agency, partner NGO | Pilot notes
September | Fieldwork: survey, focus groups, key informant interviews, records review. | Agency | Clean data set
October | Analysis and draft report, with limitations and recommendations. | Agency | Draft report
November | Review draft with implementing partner; write management response. | CSR team, partner | Comments; action tracker (sheet 8)
December | Final report and executive summary; CSR Committee review. | CSR Committee | Final report
January | Place reports before the Board. | Board | Board minutes
February | Feed findings into next year’s Annual Action Plan and budget. | CSR Committee | Revised action plan
March to annual report | Publish full reports on the website; annex the executive summary and web link to the annual report on CSR. | Company secretary | Annual report on CSR; web page